## Comm Mgt Plan Template
Communications plan template for project:
Communications item forum (What) | Owner (Who-Sender) | Audience (Who-Receiver) | Timing (When) | Format medium (How) (Where) | Purpose (Why)
Weekly project status meeting | Project Manager | Key stakeholders | Weekly, Wednesdays at 2:00 PM | Main conference room | Review status, discuss issues/risks, project deliverables
Sponsor 1:1 meeting | Project Manager | Project Sponsor | Weekly | Sponsor's office | Update on project status, discuss support needed
Weekly project status report | Project Manager | All key stakeholders | Due by Friday at 10:00 AM | Email | Provide overview of key project status issues
Change control board (CCB) meeting | Project Manager | All key stakeholders | Bi-weekly on Mondays at 10:00 AM | Main conference room | Review change requests; approve or disapprove
Vendor source selection meeting | Project Manager | Vendor representatives | One-time on Mar 11 at 10:00 AM | Sarah's office | Finalize vendor selection
Training roster confirmation | Project Manager | Training team | Continuous | Sarah's office | Finalize training roster to maximize attendance
Version: 01 |  |  | Date: