## Product Backlog
Product Backlog for Project
User Story Identifier | Priority | Category | Team | Role | Need | Value | Acceptance 1 | Acceptance 2 | Acceptance 3 | Acceptance 4 | Story Points | Comments
1 | 1 | Leadership | App Dev 1 | As an AHI leader | I need to identify and understand current segments | To target and engage with emerging markets | Access to data feeds | Provide on-demand reports |  |  | 3 | Sprint 1
2 | 1 | Marketing | App Dev 1 | As a Marketing Analyst | I need to track current market trends in real-time | To generate competitive analysis data | Monitor customer interest | Calculate AHI market share | Provide on-demand reports |  | 5 | Sprint 1
3 | 1 | Finance | App Dev 1 | As a Finance Manager | I need secure order invoicing and processing | To ensure real-time inventory reporting | Provide on-demand financial metrics | Ensure secure transactions |  |  | 4 | Sprint 2
4 | 1 | IT | App Dev 1 | As an IT Specialist | I need to ensure the app interfaces with hardware | To maintain compatibility with IT upgrades | Validate hardware compatibility | Ensure storage meets operational needs |  |  | 4 | Sprint 2
5 | 1 | Customer | App Dev 1 | As an AHI customer | I need easy access to all AHI product offerings | To ensure reliable order processing | Secure invoicing | Confirmation of transactions |  |  | 2 | Sprint 1
Sprint 1

## Product Backlog Example
Product Backlog for Project
User Story Identifier | Priority | Category | Team | Role | Need | Value | Acceptance 1 | Acceptance 2 | Acceptance 3 | Acceptance 4 | Acceptance 5 | Story Points | Comments
0001 | 1 | Customer | App Dev 1 | As a Coffee Shop Customer | I need easy access to order | To save time and reduce waiting | 1. Easy access to menu | 2. Pricing for all options | 3. Secure monetary transaction | 4. Order Confirmation |  | 5 | Sprint 1
0002 | 2 | Employee | App Dev 1 | As a store employee | I need real-time access to orders | So I can prepare in a timely manner | 1. Order information clearly displayed | 2. Customer's name | 3. Desired pick-up time | 4. Special instructions | 5. Label generation | 2 | Sprint 1

## Story Points
1 Story Point | 2 Story Points | 3 Story Points | 5 Story Points | 8 Story Points
Less Complex More Complex
User Story 1
User Story 2
User Story 3
User Story 4
User Story 5

## Story Points Solution
1 Story Point | 2 Story Points | 3 Story Points | 5 Story Points | 8 Story Points
Total Story Points: 1 + 2 + 3 + 3 + 5 = 14
Less Complex More Complex
User Story 1
User Story 2
User Story 3
User Story 4
User Story 5