## Quality Mgt Plan Template
Quality management plan for project:
Part I: Project objectives (reference project charter)
1. Develop a basic app to support coffee shop customer service and operations
2. Ensure app functionality meets or exceeds competitor apps
3. Design basic app using an external vendor (2 weeks)
4. Develop version 1 of the app (4 weeks)
5. Test the app with a small customer beta group (2 weeks)
6. Launch the app (2 weeks)
7. Gather customer feedback (4 weeks
Part II: Project quality team (Project Manager, QA, QC, SME)
Name | Role | R (Responsible) | A (Accountable) | C (Consult) | I (Inform)
Ray Masters | Project Manager | X | X |  | X
Juan Gonzales | QA Lead | X |  |  | X
Marcy Jackson | QA Lead | X |  |  | X
Hiroshi Ozawa | SME |  |  | X | X
Priya Majors | SME |  |  | X | X
Keiko Tanaka | Focus Group Lead |  |  |  | X
Quality assurance activities (quality audits) |  |  | Quality control activities (quality inpections)
Audit design process |  |  | Verify final app design
Audit development process |  |  | Verify version 1 of the app
Audit final launch planning |  |  | Verify beta testing and feedback
Verify final launch checklist