## Risk Register Template
Project: Date:
# | Cause (condition/situation) | Event | Impact | Risk owner | Category | Probability risk rating | Impact risk rating | Risk score | Trigger | Response
1 | Lack of management support | Project delays | Schedule delays | Project Manager | Threat | 4 | 5 | 20 | Low engagement from staff | Increase stakeholder engagement
2 | Unclear app requirements | Scope creep | Increased costs | Project Manager | Threat | 3 | 4 | 12 | Frequent requirement changes | Conduct regular scope reviews
3 | Limited availability of resources | Delayed project timelines | Inability to meet deadlines | HR Manager | Threat | 5 | 4 | 20 | High workload on team | Hire temporary staff if needed
4 | External vendor performance | Quality issues with app | Reduced customer satisfaction | Vendor Manager | Threat | 3 | 5 | 15 | Poor vendor feedback | Implement stricter vendor evaluations
5 | Poor training for staff | Ineffective app usage | Decreased productivity | Training Lead | Threat | 2 | 4 | 8 | Low training attendance | Schedule mandatory training sessions
6 | Inadequate testing | Bug reports post-launch | Increased costs and delays | PQA Lead | Threat | 4 | 5 | 20 | Bugs reported by beta users | Enhance testing procedures
7 | Skilled personnel availability | Talent shortage for development | Project delays | Project Manager | Opportunity | 2 | 3 | -6 | High unemployment rates | Recruit from local talent pools
Total Risk Score | [8 empty] | Risk Exposure
|  | Probability risk rating |  | Impact risk rating
|  | 5: High |  | 5: High
|  | 4: High to moderate |  | 4: High to moderate
|  | 3: Moderate |  | 3: Moderate
|  | 2: Moderate to low |  | 2: Moderate to low
|  | 1: Low |  | 1: Low